## Sheet1
Cost Estimate
Project Name: Home Essential Emporium- The Household Retail Store |  |  | Date: 03/17/2024
Note: Enter your WBS, hours, labor rates, etc. Add/delete rows and columns as needed and check all formulas (bolded below).
| Internal | $/hour | Internal | External | $/hour | External | Total | Non-labor $ | Total Cost
WBS Categories | Labor |  | $ Total | Labor |  | $ Total | Labor
1. Initiating | 150 | 60 | 9000 |  |  | 0 | 9000 |  | 9000
2. Planning | 500 | 60 | 30000 |  |  | 0 | 30000 |  | 30000
3. Executing |  |  | 0 |  |  | 0 | 0 |  | 0
3.1 Frontend design and implementation |  |  | 0 |  |  | 0 | 0 |  | 0
3.1.1 Homepage | 80 | 60 | 4800 |  |  | 0 | 4800 |  | 4800
3.1.2 Admin Dashboard | 80 | 60 | 4800 |  |  | 0 | 4800 |  | 4800
3.1.3 Search page | 80 | 60 | 4800 |  |  | 0 | 4800 |  | 4800
3.1.4 User Dashboard | 80 | 60 | 4800 |  |  | 0 | 4800 |  | 4800
3.1.5 Cart and payment gateway | 80 | 60 | 4800 |  |  | 0 | 4800 |  | 4800
3.2.Backend Implementation (API design and integration) | 500 | 60 | 30000 |  |  | 0 | 30000 |  | 30000
3.3 Testing | 300 | 55 | 16500 |  |  | 0 | 16500 |  | 16500
3.4 Payment Gateway | 300 | 55 | 16500 | 3 | 250 | 750 | 17250 |  | 17250
3.5 Deployment and Stakeholder Communication | 300 | 55 | 16500 |  |  | 0 | 16500 |  | 16500
4. Monitoring and Controlling | 500 | 55 | 27500 |  |  | 0 | 27500 |  | 27500
5. Closing | 200 | 55 | 11000 |  |  | 0 | 11000 |  | 11000
Subtotal | [8 empty] | 181750
Reserves |  |  | 0 |  |  | 0 | 0 |  | 18175
Total | 3150 |  | 181000 | 3 | 250 | 750 | 181750 | 0 | 199925
Assumptions
Labor Rates:
- Project Manager: $60/ hour
- Developers: $55/hour
- UI/ UX Developer: $55/hour
Duration of the Project: 2.5 months
Contingency Reserves: $18,175.0